## Sheet1
|  | Aug 13-28 |  |  | Aug29-Sep27 |  |  |  | Oct 1-31 | [10 empty] | Nov 1-15
|  | 13-14 | 14-20 Aug | 21-28 Aug | 29-3 Sep | 4-10 Sep | 12-18 Sep | 26-27 | 1-4 Oct | 5-6 O | 7-9 Oct | 10-13 O | 14-15 | 16-18 O | 19-20 | 21-25 Oct | 26-27 | 28-29 | 30-31 | 1-2 N | 3-6 Nov | 7-8 N | 9-12 Nov | 13-15 N
Team Formation
Brain stoming
PREPARATION | Project decision or idea
Rules and regulations
Features Discussion
Project Statement
REQUIREMENT PHASE | Feasibility and Rejection report
Decision of SDLC model and Questions for survey
Questionaires and surveys
[All] Design
[All] Initialise project
[Server] User Account
MILESTONE-1 | [CA,Extension] User login and Register
[Extension,Server] Highlighting
[CA] List highlights of User
[All] Testing
[All] Design
MILESTONE-2 | [Server,CA] Create note on demand
[Server,Extension]Adding tags and categories to highlights with search features
[CA] Search features
[All] Testing
[All] Design
MILESTONE-3 | [Extension] Rehighlighting text in browsers
[Extension] Highlight in google search
[All]Commenting feature on Highlight with edit document
[All] Testing
MILESTONE-4 | [All] Finalising documentation
[All] Deployment